State of the Network
BornHack 2017
NOC Team
noc@bornhack.org

---
Important stuff
So, we think you should know!
- We do NOT collect data for “fun” (or profit)
- We respect your privacy
- NO packet captures, except for solving problems
  We dont even have central mirror port for sniffing pre-configured
- NO IDS or traffic analysis, not even netflow
- DHCPD has the MAC addresses, but only HLK has access, and will delete before leaving BH
- UniFi controller has MAC addresses, but will ALSO be deleted before leaving BH
- Note: Upstream ISP required by law to do some logging in DK

---
Preparations
Before getting here, we did:
- Asked RIPE NCC for IPv4, IPv6 and AS number
- Asked Bornfiber Peter Krupl for assistance in configuring uplink, thank you Peter
- Gathered some devices, cables, found the ones from last year
- Created a NOC team on the BornHack page
  but forgot to plan when those people would arrive :-)

---
Hardware used
- Core switching Juniper EX3300
- Core routing Juniper SRX240
  (next year OpenBSD if I am doing it)
- PoPs made with boxes from the BRK
- Wired Brocade switches in PoPs
  Three series and OLD, SSH needs insecure config to connect
- Wifi Ubiquity UniFi AP Pro, AC Lite, and old AP
- Service VMs on VMware ESXi, shout out to Tobias for providing server and help

---
Major problems
Beginning:
- DHCP floods, ARP floods, duplicates
  AP=> switchport misconfiguration and wirelessly uplinked APs
- Power outages, rain and water
- Fiber converter, fried by thunder
- Didn't got around to making the 802.1x – very sorry

---
Minor problems
- UniFi Controller, some wireless uplinks by default
- Relearning my Brocade skills, will forget them in a week
- Rogue DHCP server, will need to have better switches/switchport security
- Some other funky DHCP problems reported by a few users, but “works for me” was checked on tent by Morten
- GeoIP puts us in Germany, always a problem for temp networks

---
Flooding

---
Succes and achivements
- With NOC supporter help we have solved lots of problems, made new friends, learned $stuff
- Built a network spanning 350m from North1 PoP to South3 PoP
- 8 PoPs including the core room with server hosting
- Put out MORE than 1km of network cable to connect main sites, achievement unlocked :-) around 900m fiber, rest copper
- Provided a reasonable stable network with some people reporting 480Mbps/620Mbps at times
- Some phones reported 8ms latency and 220/220Mbps on wireless, monday before the event really started
- My phone has reported 150/150Mbps during event at times, mostly latency has been in range of 8-20ms – to Copenhagen servers
- Lot more usage than last year, use moar bandwidth

---
PoPs / datenklos

---
LibreNMS switches

---
Wireless 12 APs working

---
UniFi is pretty easy, and “OK”
UniFi is pretty easy, and “OK”

---
Some stats
- UniFi controller reports 469 clients seen!
- One client has downloaded 128Gb :-)
- Another client uploaded 40Gb

---
Bandwidth and power outage

---
Lessons learned
- Second year, was not prepared enough
- Project requires NOC architects, Server people, NOC Helpdeskers – initially we had me on-site on Sunday and Monday…
- BUT then 8 people showed up and helped, sorry for not remembering all names, but Mortenx2, Eightdot etc. you saved me/us!
- Goal next year, have 2x JN-CIS SP, 2x server people, +5 NOC support
- Bring more fiber converters, one fried and cheap

---
PEG DHCP
PEG DHCP RFC2322 was implemented https://en.wikipedia.org/wiki/Peg_DHCP
- PEG DHCP worked REALLY well, “DHCP giving you problems, take a peg, done”
- Make PEGs for wifi and wired, two colors
  We are splitting this up next year

---
Conclusion
- We did it, there was a network
- We need more preparation, pre-camp NOC setup meeting

---
Some software tools used
- UniFi Controller running on Ubuntu, easy
- OpenBSD conserver, DHCPD and other stuff
  http://conserver.com/ - serial connections
- LibreNMS for stats – autodiscover yay!
  https://www.librenms.org/
- Oxidized for getting config from devices
  https://github.com/ytti/oxidized
- Plus usual suspects, tcpdump, wireshark, ping, nmap, traceroute